## User Stories
| Main User Story | Sub-Task
1 | Flight | Add flight
View flight
Cancel flight
Modify flight
2 | Schedule | Add Schedule
View Schedule
Cancel Schedule
Modify Schedule
3 | Routes | Add Routes
View Routes
Cancel Routes
Modify Routes
4 | Booking | add booking
view Booking
cancel/modify booking
5 | User | create account
login
check flights
booking seats
6 | Authentication | Registration
Login

## Nikhil
Task No. | Task Name | Estimated hours/Time | Actual Time Taken | Allotted on day | Comments
1. Create Account
1.1 | Add User Details
1.1.1 | code | 2 |  | Tuesday(04-aug)
1.1.2 | Validation+Exception Handling | 1 |  | Tuesday(11-aug)
2. User Login
2.1 | Login
2.1.1 | code | 2 |  | Tuesday(04-aug)
2.1.2 | Validation+Exception Handling | 1 |  | Tuesday(11-aug)
3. create Passenger
3.1 | add passenger
3.1.1 | code | 2 |  | Monday(10-Aug)
3.1.2 | Validation+Exception Handling | 1 |  | Tuesday(11-aug)
4. Booking
4.1 | Modify/cancel Booking
4.1.1 | code | 2 |  | Tuesday(10-Aug)
4.1.2 | Validation+Exception Handling | 1 |  | Tuesday(11-aug)

## Dinakar
Task No. | Task Name | Estimated hours/Time | Actual Time Taken | Allotted on day | Comments
1 | Booking Details
1.1 | Add Booking
1.1.1 | code | 2 |  | Tuesday(04-aug)
1.1.2 | Validation+Exception Handling | 1 |  | Tuesday(11-aug)
1.2 | View Booking
1.2.1 | code | 2 |  | Tuesday(04-Aug)
1.2.2 | Validation+Exception Handling | 1 |  | Tuesday(11-aug)
2. View available Flights
2.1 | View Fflights
2.1.1 | code | 2 |  | Monday(10-Aug)
2.1.2 | Validation+Exception Handling | 1 |  | Tuesday(11-aug)

## Madhurima
Task No. | Task Name | Estimated hours/Time | Actual Time taken | Allotted on day | Comments
1 | Flight
1.1 | Add Flight
1.1.1 | Code | 2 |  | Tuesday(4th-Aug)
1.1.2 | Validation + Exception Handling | 1 |  | Tuesday(11th-Aug)
1.2 | View Flight
1.2.1 | Code | 2 |  | Tuesday(4th-Aug)
1.2.2 | Validation + Exception Handling | 1 |  | Tuesday(11th-Aug)
1.3 | Cancel Flight
1.3.1 | Code | 2 |  | Tuesday(4th-Aug)
1.3.2 | Validation + Exception Handling | 1 |  | Tuesday(11th-Aug)
1.4 | Modify Flight
1.4.1 | Code | 2 |  | Tuesday(4th-Aug)
1.4.2 | Validation + Exception Handling | 1 |  | Tuesday(11th-Aug)
2 | Authentication
2.1 | Login
2.1.1 | Code | 2 |  | Monday(10th-Aug)
2.1.2 | Validation + Exception Handling | 1 |  | Tuesday(11th-Aug)

## Samyuktha
Task No. | Task Name | Estimated hours/Time | Actual Time Taken | Allotted on day | Comments
1 | Schedule Details
1.1 | Add Schedule
1.1.1 | code | 2 |  | Tuesday(04-aug)
1.1.2 | Validation+Exception Handling | 1 |  | Tuesday(11-aug)
1.2 | View Schedule
1.2.1 | code | 2 |  | Tuesday(04-Aug)
1.2.2 | Validation+Exception Handling | 1 |  | Tuesday(11-aug)
1.3 | Modify Schedule
1.3.1 | code | 2 |  | Tuesday(04-Aug)
1.3.2 | Validation+Exception Handling | 1 |  | Tuesday(11-aug)
1.4 | Cancel Schedule
1.4.1 | code | 2 |  | Tuesday(04-Aug)
1.4.2 | Validation+Exception Handling | 1 |  | Tuesday(11-aug)
2 | Route Details
2.1 | Add Routes
2.1.1 | code | 2 |  | Monday(10-Aug)
2.1.2 | Validation+Exception Handling | 1 |  | Tuesday(11-aug)
2.2 | View Routes
2.2.1 | code | 2 |  | Monday(10-Aug)
2.2.2 | Validation+Exception Handling | 1 |  | Tuesday(11-aug)
2.3 | Modify Routes
2.3.1 | code | 2 |  | Monday(10-Aug)
2.3.2 | Validation+Exception Handling | 1 |  | Tuesday(11-aug)
2.4 | Cancel Routes
2.4.1 | code | 2 |  | Monday(10-Aug)
2.4.2 | Validation+Exception Handling | 1 |  | Tuesday(11-aug)